## Project Matrix
Jefferson County Parks and Recreation Capital Projects
Last updated: | 2016-05-01 |  | Total | 44.4 | 64.9 | 456 | 71.5 | 34 | 0 | 55 | 0 | 673.8 | [6 empty] | Weight factors can be adjusted as needed. Scores will automatically recalculate
[19 empty] | Benefit | [5 empty] | Effort
[14 empty] | 0 |  |  |  | Weight Factor | 40% | 20% | 20% | 10% | 10% |  | 50% | 20% | 20% | 10%
|  |  |  | Estimated Spending ($K) | [7 empty] | Columns E - L (hidden) contain spending plan |  |  |  | Easy project that can be done quickly with volunteer labor and donations or is already funded |  |  | 1=Nice to have 3=Needed to prevent minor deterioration 9=Mandatory or required to prevent significant deterioration | 1=Minimal impact 3=Moderate impact on utilization or accessibility 9=Mandatory(ADA), significant impact on utilization or accessibility or satisfies a major unmet need | 1=Primarly Local Use, limited flexibility 3=Regional attraction, multiple uses 9=Draws out of area users, multiple uses, significant improvement of demographic or geographic equity | 1=Minimal impact 3=Modest impact on local economy 9=Significant economic benefits to local or regional economy | 1=Minimal impact 3=Moderate impact to 1 category 9=Significant impact to 1 categotry or moderate impact to 2 or more |  | 1=<$500 3=$500 - $15,000 9=>$15000 | 1=Less than 30 days, no acceptance or permit obstacles 3=Less than 12 months, minor permit or acceptance obstacles 9=Greater than 12 months, significant challenges likely | 1=No staff req'd, volunteer labor secured 3=Minimal staff req'd, volunteer labor likely 9=Significant staff, volunteer labor unknown | 1=O&M can be done with volunteer labor and donations 3=O&M less than $500/yr 9=O&M>$500/yr, chronic problem
Location | Item | Notes | Scope | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2025 | 2035 | Initial Cost Estimate, $K | Prioritize?, Y/N | Estimated Annual O&M Expense | Grant potential, Y/N | On "Check it off list", Y/N | Created / Start Date | Status | Saves what we have | Improves what we have | Level and Equity of use | Economic Benefit | Health and Safety (People, Community, Environment) | Total Benefit Score | Overall Net Project Cost (factor in grant potential) | Complexity and timeline | Human resource needs | Sustainability | Total Effort Score | BE Ratio | Comments | Timing/Urgency | Improvement or Repair? | Completion Date
North Beach | Shelter repair | Maybe 4 years left on old roof | Replace Roof, Post | 0.5 | [6 empty] | 45 | 0.5 | Y |  | N | Y |  |  | 9 | 3 | 9 | 3 | 3 | 6.6 | 1 | 1 | 3 | 1 | 1.4 | 4.7143 |  | 2 - 4 years | Repair
Oak Bay Campground | Repair kiosk at Lower Oak Bay Campground | Volunteer - Greg Graves | Clean and paint panel, repair plexi-glass cover, sand & seal structural members, update and improve signage | [14 empty] | In progress | 9 | 3 | 1 | 1 | 1 | 4.6 | 1 | 1 | 1 | 1 | 1 | 4.6 | Panel cleaned and painted, plexi-glass door repaired. | 12 months | Repair
Irondale Beach Park | Loop Path |  | Build and improve park Loop path |  |  |  | 4 |  |  |  |  | 4 | Y |  | Y |  |  | In progress | 3 | 9 | 9 | 1 | 3 | 5.2 | 1 | 3 | 1 | 1 | 1.4 | 3.7143 | Apply to RCO in 2016 | 2 - 4 years | Improvement
North Beach | Park Partitions and Parking Lot Improvements |  | Replace with Rocks, Grade and Parking Stops |  |  |  | 6 |  |  |  |  | 4 | Y |  | Y | N |  |  | 9 | 3 | 1 | 1 | 3 | 4.8 | 1 | 1 | 3 | 1 | 1.4 | 3.4286 |  | 2 - 4 years | Improvement
North Beach | New Sign | Replace Sign, the old one fell down | [16 empty] | 9 | 3 | 1 | 1 | 1 | 4.6 | 1 | 1 | 3 | 1 | 1.4 | 3.2857 |  | 12 months
Quilcene Campground | Shelter | URGENT Roof Leaking, caving in | Replace Roof, Treat Beetles | 12 | [7 empty] | 12 | Y |  |  | Y |  |  | 9 | 1 | 1 | 1 | 3 | 4.4 | 1 | 1 | 3 | 1 | 1.4 | 3.1429 | Request GF Budget Extension | 12 months | Repair
Lake Leland | Build Bank Fishing Trail | Part of DFW project | [16 empty] | 3 | 9 | 3 | 1 | 3 | 4 | 1 | 3 | 1 | 1 | 1.4 | 2.8571 | Contingent on DFW project | 2 - 4 years
Irondale Community Park | Repair and Paint Toilet | Volunteer or staff | Paint, repair door |  | 0.5 | [6 empty] | 0.5 | N |  |  | Y |  |  | 9 | 1 | 1 | 1 | 3 | 4.4 | 1 | 1 | 3 | 3 | 1.6 | 2.75 | Recruit volunteers | 12 months | Repair
Gibbs Lake | Park Specific Signage | Great opportunity | Comprehensive update |  |  | 4 | [5 empty] | 4 | Y | [5 empty] | 1 | 9 | 9 | 3 | 3 | 4.6 | 1 | 3 | 3 | 1 | 1.8 | 2.5556 |  | 2 - 4 years | Improvement
Oak Bay Campground | Repair and Paint Lower Toilet | Greg Graves volunteer | Paint inside & outside | 0.1 | [7 empty] | 0.1 | N |  |  | Y |  |  | 9 | 1 | 3 | 1 | 1 | 4.6 | 1 | 3 | 3 | 1 | 1.8 | 2.5556 | Greg Graves - spring 2016 | 12 months | Repair
HJ Carrol Park | Install new Bouldering Area | [17 empty] | 1 | 9 | 3 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 1.2 | 2.5 | To be done by donation | 12 months | Improvement
HJ Carrol Park | BMX Track | Ideal for volunteer group | Rebuild and or reconfigure |  |  | 3.5 |  |  | 5 |  |  | 8.5 | Y | [5 empty] | 9 | 9 | 3 | 1 | 3 | 6.4 | 1 | 3 | 3 | 9 | 2.6 | 2.4615 | Ideal Community Project - facilitate | 2 - 4 years | Repair
Chimacum Park | Clean Shelter, repair or replace roof |  | Clean, replace roof |  | 12 | [6 empty] | 12 | N | [5 empty] | 9 | 1 | 1 | 1 | 3 | 4.4 | 1 | 3 | 3 | 1 | 1.8 | 2.4444 | Recruit volunteers | 12 months | Repair
North Beach | Shelter | Not Urgent - This Shelter is relatively strong | Replace entire structure | [8 empty] | 45 | [6 empty] | 9 | 3 | 9 | 3 | 3 | 6.6 | 3 | 3 | 3 | 1 | 2.8 | 2.3571 |  | >4 years | Repair
Memorial Field | Replace Quincy St Fence | Friends Project | Replace | [8 empty] | 0 | N |  |  | Y |  |  | 9 | 1 | 1 | 1 | 3 | 4.4 | 3 | 1 | 1 | 1 | 2 | 2.2 | Facilitate the Project with Friends | 12 months | Repair
Lake Leland | Restore Grounds in Campground | Volunteer project | [9 empty] | 0 | N |  |  | Y |  | Done | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 1 | 3 | 1 | 1.4 | 2.1429 |  | Done | Repair
PT Rec Center | Replace Playground fence | URGENT | Replace Fence |  | 4 | [6 empty] | 4 | Y | [5 empty] | 9 | 3 | 1 | 1 | 9 | 5.4 | 3 | 1 | 3 | 3 | 2.6 | 2.0769 | Recruit volunteers | 12 months | Repair
HJ Carrol Park | Improve floor in Salmon Shelter |  | Remove loose gravel, replace with compacted crushed basalt | [12 empty] | Y |  |  | 3 | 9 | 3 | 1 | 3 | 4 | 3 | 1 | 1 | 1 | 2 | 2 | Volunteer (Greg Graves) | 12 months | Improvement
HJ Carrol Park | Improve ADA access |  | Install compacted crushed rock walkway surface between parking and selected areas at fields and shelters | [12 empty] | Y |  |  | 1 | 9 | 9 | 3 | 3 | 4.6 | 3 | 1 | 3 | 1 | 2.4 | 1.9167 | Develop plan | 2 - 4 years | Improvement
Lake Leland | Replace Dock | URGENT | Replace |  | 26 | [6 empty] | 26 | Y | [5 empty] | 9 | 1 | 3 | 3 | 9 | 5.6 | 3 | 3 | 3 | 3 | 3 | 1.8667 | Pursue with F&W | 12 months | Repair
Indian Island Park | Replace Shelter | SEMI URGENT | Replace, reconfigure parking and greenspace areas. | [6 empty] | 75 |  | 75 | Y | [5 empty] | 9 | 3 | 3 | 1 | 3 | 5.2 | 3 | 3 | 3 | 1 | 2.8 | 1.8571 | Evaluate reconfiguration of entire area to improve safety and traffic flow | 2 - 4 years | Improvement
HJ Carrol Park | Replace signs on "Salmon Trail" | [17 empty] | 3 | 1 | 1 | 1 | 1 | 1.8 | 1 | 1 | 1 | 1 | 1 | 1.8 | Boy scouts? | 12 months | Repair
Indian Island Park | Install information kiosk at Portage Shelter trailhead | [17 empty] | 1 | 3 | 3 | 1 | 1 | 1.8 | 1 | 1 | 1 | 1 | 1 | 1.8 |  | 2 - 4 years | Improvement
Indian Island Park | Develop unimproved Loop Trail in Portage upland forest area to add interest | [17 empty] | 1 | 3 | 3 | 1 | 1 | 1.8 | 1 | 1 | 1 | 1 | 1 | 1.8 | Develop route and plan | 2 - 4 years | Improvement
Memorial Field | Stadium spalling repair |  | Spalling Repair |  |  | 50 | [5 empty] | 50 | Y | [5 empty] | 9 | 1 | 3 | 3 | 3 | 5 | 3 | 3 | 3 | 1 | 2.8 | 1.7857 |  | 12 months | Repair
Equestrian Park | Fencing and Trails | JEA | Install N. Perimeter + Trails |  | 0 | [6 empty] | 0 | Y | [5 empty] | 1 | 9 | 9 | 3 | 3 | 4.6 | 1 | 9 | 1 | 1 | 2.6 | 1.7692 | This ranking assumes the JEA is completing the project. | >4 years | Improvement
PT Rec Center | Repair and Paint Games Room/Rest Room | Farmers Market reliance on RR | Paint, floor, RR Dividers, repairs |  | 12 | [6 empty] | 12 | N | [5 empty] | 3 | 3 | 1 | 1 | 3 | 2.4 | 1 | 1 | 3 | 1 | 1.4 | 1.7143 | Recruit volunteers | 12 months | Repair
HJ Carrol Park | Remove invasives along perimeter trail and in vacant area near BMX track and BB court | [14 empty] | Y |  |  | 3 | 3 | 1 | 1 | 3 | 2.4 | 1 | 1 | 3 | 1 | 1.4 | 1.7143 | Recruit volunteers | 2 - 4 years | Repair
Quilcene Campground | Install Safety Light | Contractor |  | 0.3 |  | 1.5 | [5 empty] | 1.8 | N | [5 empty] | 1 | 3 | 1 | 1 | 3 | 1.6 | 1 | 1 | 1 | 1 | 1 | 1.6 |  | 12 months | Improvement
HJ Carrol Park | Remove alders by playground | [14 empty] | Y |  |  | 3 | 3 | 1 | 1 | 1 | 2.2 | 1 | 1 | 3 | 1 | 1.4 | 1.5714 | Recruit volunteers | 12 months | Improvement
Irondale Beach Park | Improve Paths | Volunteers and RCO Project | Improve park paths |  |  |  | 4 |  |  |  |  | 4 | N |  |  | Y |  | In progress | 3 | 3 | 3 | 1 | 3 | 2.8 | 1 | 3 | 3 | 1 | 1.8 | 1.5556 | Recruit volunteers | 12 months | Improvement
Quilcene Campground | Courts | Project underway | Resurface and paint |  |  | 30 | [5 empty] | 30 | Y |  |  |  |  | In progress | 9 | 3 | 1 | 1 | 1 | 4.6 | 3 | 3 | 3 | 3 | 3 | 1.5333 |  | Done
Chimacum Park | Entire Park | Quick Fix Up for Safety and Community | Clean, Trees, Hardscape, Repair RR | [8 empty] | 0 | N | [5 empty] | 3 | 3 | 1 | 1 | 3 | 2.4 | 1 | 1 | 3 | 3 | 1.6 | 1.5 | Recruit volunteers | 12 months | Improvement
Irondale Community Park | Playground | Replace Slides | Replace |  | 4 | [6 empty] | 4 | Y | [5 empty] | 9 | 1 | 1 | 1 | 3 | 4.4 | 3 | 3 | 3 | 3 | 3 | 1.4667 | Apply to RCO in 2016 | 12 months | Repair
North Beach | Preserve Restroom | Restroom Building is at risk | Save the building, restore to function | 3 | [5 empty] | 50 |  | 1 | N | [5 empty] | 9 | 1 | 1 | 3 | 3 | 4.6 | 1 | 3 | 9 | 3 | 3.2 | 1.4375 |  | 12 months | Repair
Gibbs Lake | Generator Building | Caretaker | Remove | [6 empty] | 4 |  | 4 | N | [5 empty] | 3 | 1 | 1 | 1 | 3 | 2 | 1 | 1 | 3 | 1 | 1.4 | 1.4286 |  | 2 - 4 years | Improvement
Lake Leland | Repair or Replace Day Use Toilet | Replace Day Use Toilet |  | 1 | [7 empty] | 1 | N | [5 empty] | 3 | 1 | 1 | 1 | 3 | 2 | 1 | 1 | 3 | 1 | 1.4 | 1.4286 |  | 12 months | Repair
Memorial Field | Repair Dugouts | Irene in 2015 | In - House repairs |  |  | 2 |  |  |  | 5 |  | 7 | N | [5 empty] | 3 | 1 | 1 | 1 | 3 | 2 | 1 | 1 | 3 | 1 | 1.4 | 1.4286 |  | 12 months | Repair
North Beach Park | Reconfigure |  | Reconfigure for traffic calming and parking improvements | 13 | [7 empty] | 13 | [6 empty] | 3 | 9 | 3 | 1 | 3 | 4 | 3 | 3 | 3 | 1 | 2.8 | 1.4286 |  | 2 - 4 years | Improvement
Indian Island Park | Provide "ADA access at trailheads | [17 empty] | 1 | 9 | 3 | 1 | 3 | 3.2 | 3 | 1 | 3 | 1 | 2.4 | 1.3333 |  | 2 - 4 years | Improvement
Hicks Park | Parking Lot | Roads Crew | Grade | 0.5 | [7 empty] | 0.5 | N |  |  |  |  | Done | 3 | 1 | 1 | 1 | 1 | 1.8 | 1 | 1 | 3 | 1 | 1.4 | 1.2857 |  | Done | Improvement
Irondale Community Park | Repair and paint Pumphouse | Volunteers needed | Paint and repair |  | 0.5 | [6 empty] | 0.5 | N |  |  | Y |  |  | 3 | 1 | 1 | 1 | 1 | 1.8 | 1 | 1 | 3 | 1 | 1.4 | 1.2857 | Recruit volunteers | 12 months | Repair
Irondale Community Park | Backstop | Fencing contractor | Repair | 2 | [7 empty] | 2 | N |  |  |  |  | Done | 3 | 1 | 1 | 1 | 1 | 1.8 | 1 | 1 | 3 | 1 | 1.4 | 1.2857 |  | 12 months | Repair
Oak Bay Campground | Provide brochure at kiosks with description of nearby attractions/activities and directions to IIP trails | [17 empty] | 1 | 3 | 3 | 1 | 1 | 1.8 | 1 | 1 | 3 | 1 | 1.4 | 1.2857 | Develop brochure, place boxes on kiosks at Oak Bay | 12 months | Improvement
Quilcene Campground | Campground Utilities | Revenue enhancer | Water and Power |  |  | 20 | 20 |  |  |  |  | 40 | Y | [5 empty] | 1 | 9 | 9 | 9 | 1 | 5 | 3 | 9 | 3 | 3 | 4.2 | 1.1905 |  | >4 years | Improvement
HJ Carrol Park | Repair Athletic Field irrigation | Staff | Repair irrigation |  | 2.5 | 2.5 | 2.5 |  |  |  |  | 7.5 | N | [5 empty] | 3 | 1 | 1 | 1 | 3 | 2 | 1 | 3 | 3 |  | 1.7 | 1.1765 |  | 12 months | Repair
Equestrian Park | Event Ring and Toilet | JEA | Install |  |  | 0 | [5 empty] | 0 | Y | [5 empty] | 1 | 9 | 3 | 3 | 1 | 3.2 | 3 | 3 | 3 | 1 | 2.8 | 1.1429 | Postpone until more information | >4 years | Improvement
Equestrian Park | Trails | JEA Volunteers needed | Improve existing | [8 empty] | 0 | N | [5 empty] | 1 | 9 | 3 | 3 | 1 | 3.2 | 3 | 3 | 3 | 1 | 2.8 | 1.1429 | Postpone until more information | >4 years | Improvement
Gibbs Lake | Generator Building |  | Remove |  |  |  | 3 |  |  | 4 |  | 7 | Y | [5 empty] | 3 | 1 | 1 | 1 | 3 | 2 | 1 | 3 | 3 | 1 | 1.8 | 1.1111 |  | 2 - 4 years | Improvement
Trailhead Park | Single Track Improvements |  | Hikers, Bikers and Horses | [8 empty] | 0 | Y | [5 empty] | 1 | 3 | 3 | 1 | 3 | 2 | 1 | 3 | 3 | 1 | 1.8 | 1.1111 | Pursued by Backcountry Horsemen | >4 years | Improvement
HJ Carroll | New Soccer Goals | Full Sized | 4 New Goals | 9 |  |  |  | 9 |  |  |  | 18 | [6 empty] | 3 | 3 | 1 | 1 | 1 | 2.2 | 3 | 1 | 1 | 1 | 2 | 1.1 |  | 12 months | Repair
Gibbs Lake | New Trail Network with some bicycle only trails | Quimper Trails, Volunteers needed to help them | Plan then Build | [8 empty] | 0 | Y |  |  | Y |  | In progress | 1 | 3 | 3 | 3 | 3 | 2.2 | 1 | 3 | 3 | 3 | 2 | 1.1 |  | 12 months | Improvement
Indian Island Park | Portage Parking Lot | Roads Crew | Grade & Partition | 0 |  | 4 | [5 empty] | 4 | N | [5 empty] | 3 | 3 | 1 | 1 | 9 | 3 | 3 | 3 | 3 | 1 | 2.8 | 1.0714 |  | 2 - 4 years | Improvement
Irondale Beach Park | Interpretive signage | RCO, Volunteers, Partners | Signage, displays, trails |  | 12 |  | 12 |  |  |  |  | 24 | Y |  | Y |  |  |  | 1 | 9 | 3 | 1 | 1 | 3 | 3 | 3 | 3 | 1 | 2.8 | 1.0714 |  | 2 - 4 years | Improvement
Lake Leland | Improve signage on highway |  | Install new signs on highway to improve access to park and campground | [15 empty] | 1 | 9 | 3 | 1 | 1 | 3 | 3 | 3 | 3 | 1 | 2.8 | 1.0714 |  | 2 - 4 years | Improvement
Quilcene Campground | RV Dump | Revenue enhancer | Install |  |  | 35 | [5 empty] | 35 | Y | [5 empty] | 1 | 9 | 3 | 3 | 1 | 3.2 | 3 | 3 | 3 | 3 | 3 | 1.0667 |  | >4 years | Improvement
HJ Carrol Park | ADA | RCO | Improve parking and paths | 0 |  |  | 35 |  |  |  |  | 35 | Y |  | Y | Y |  |  | 1 | 9 | 3 | 1 | 3 | 3.2 | 3 | 3 | 3 | 3 | 3 | 1.0667 | Apply to RCO in 2016 | 12 months | Improvement
Gibbs Lake | Forest | Dog Hair forest in places | Release thin for park values | [8 empty] | 0 | Y | [5 empty] | 3 | 3 | 3 | 1 | 3 | 2.8 | 3 | 3 | 3 | 1 | 2.8 | 1 |  | >4 years | Improvement
Irondale Beach Park | Hardscaping/Landscaping | Volunteers and RCO Project | Drainage, walls, dirt |  |  |  |  | 4 |  |  |  | 4 | Y |  | Y |  |  |  | 3 | 3 | 3 | 1 | 3 | 2.8 | 3 | 3 | 3 | 1 | 2.8 | 1 |  | 2 - 4 years | Improvement
Irondale Beach Park | Native vegetation | DNR, Volunteers, possible RCO Combine with trail | 50% Complete |  | 2 | [6 empty] | 2 | N |  |  | Y |  | In progress | 3 | 3 | 3 | 1 | 3 | 2.8 | 3 | 3 | 3 | 1 | 2.8 | 1 | Received two grants and project will be complete in 2016 | 12 months | Improvement
Trailhead Park | Forest | Partners? | Release thin for park values | 4 | 4 | 4 | 4 | 4 |  | 4 |  | 24 | Y | [5 empty] | 3 | 3 | 1 | 1 | 3 | 2.4 | 3 | 1 | 3 | 1 | 2.4 | 1 |  | 2 - 4 years | Improvement
Oak Bay Campground | Widen Exit Road |  | Widen and reconfigure so one gate | 8 | [7 empty] | 8 | [6 empty] | 3 | 3 | 1 | 1 | 3 | 2.4 | 3 | 1 | 3 | 1 | 2.4 | 1 |  | 2 - 4 years | Improvement
All Campgrounds | New Iron Rangers |  | Lockable, serviceable by volunteers | 4 | [7 empty] | 4 | [6 empty] | 3 | 3 | 1 | 1 | 3 | 2.4 | 3 | 1 | 3 | 1 | 2.4 | 1 |  | 2 - 4 years | Improvement
HJ Carrol Park | Park Specific Signage |  | Comprehensive update |  |  |  | 10 |  |  |  |  | 10 | Y | [5 empty] | 1 | 3 | 3 | 1 | 1 | 1.8 | 1 | 3 | 3 | 1 | 1.8 | 1 |  | 2 - 4 years | Improvement
HJ Carrol Park | Perimeter Path | Staff | Gravel and grade |  | 1.4 |  | 3 |  |  |  |  | 4.4 | Y |  |  | Y |  |  | 1 | 3 | 3 | 1 | 3 | 2 | 1 | 3 | 3 | 3 | 2 | 1 |  | 12 months | Repair
All | Comprehensive Signage and Branding | Critical to our future, seek hard dollars | New Logo, Sign Replacement and Park/Facility "Branding" |  | 24 | [6 empty] | 24 | Y | [5 empty] | 3 | 3 | 3 | 1 | 1 | 2.6 | 3 | 3 | 3 | 1 | 2.8 | 0.92857 |  | 2 - 4 years | Improvement
Chimacum Park | Forest Safety | Selective thinning for safety | Remove root rot firs | [6 empty] | 10 |  | 10 | Y | [5 empty] | 3 | 1 | 1 | 1 | 9 | 2.6 | 3 | 3 | 3 | 1 | 2.8 | 0.92857 |  | >4 years | Improvement
Gibbs Lake | Derelict Buildings |  | Remove |  |  |  | 27 |  |  |  |  | 27 | Y |  |  | Y |  |  | 3 | 1 | 1 | 1 | 9 | 2.6 | 3 | 3 | 3 | 1 | 2.8 | 0.92857 |  | 12 months | Improvement
HJ Carrol Park | Improve vegetation on slope between fields and perimeter trail | [17 empty] | 3 | 3 | 1 | 1 | 1 | 2.2 | 3 | 1 | 3 | 1 | 2.4 | 0.91667 | Develop plan | 2 - 4 years | Improvement
HJ Carroll | Round Planters | Reconfigure for ease of maintenance | 2 round-about style planters | 2 | [7 empty] | 2 | [6 empty] | 3 | 3 | 1 | 1 | 1 | 2.2 | 3 | 1 | 3 | 1 | 2.4 | 0.91667 |  | 12 months | Improvement
Memorial Field | Back Fence | Study options | Remove - use plants |  |  |  | 75 |  |  |  |  | 75 | Y |  |  |  |  | In Progress | 9 | 1 | 3 | 1 | 3 | 4.8 | 9 | 3 | 1 | 1 | 5.4 | 0.88889 |  | 2 - 4 years | Improvement
Oak Bay Campground | Furniture | Seek Hard Dollars | Tables, grills, fire rings, surfaces, plants | 8 | 2 | 2 | 2 | 2 | 10 |  |  | 26 | Y | [5 empty] | 3 | 3 | 3 | 1 | 1 | 2.6 | 3 | 3 | 3 | 3 | 3 | 0.86667 |  | 2 - 4 years | Improvement
Oak Bay Campground | Electric | Seek Hard Dollars | Safety, capacity, location |  | 14 |  |  | 10 |  |  |  | 24 | Y | [5 empty] | 1 | 3 | 3 | 1 | 9 | 2.6 | 3 | 3 | 3 | 3 | 3 | 0.86667 |  | >4 years | Improvement
Oak Bay Campground | Water | Seek Hard Dollars | Safety and capacity |  | 14 |  | 4 |  | 5 |  |  | 23 | Y | [5 empty] | 1 | 3 | 3 | 1 | 9 | 2.6 | 3 | 3 | 3 | 3 | 3 | 0.86667 |  | >4 years | Improvement
Oak Bay Campground | Caretakers Site Improvements |  | Septic tank, electric, water, relocate | 15 | [7 empty] | 15 | [6 empty] | 3 | 9 | 1 | 1 | 3 | 3.6 | 3 | 3 | 3 | 9 | 3.6 | 1 |  | 12 months | Improvement
PT Rec Center | Gymnasium |  | Repair or Replace | [7 empty] | 2000 | 2000 | Y | [5 empty] | 9 | 1 | 1 | 1 | 9 | 5 | 9 | 3 | 3 | 3 | 6 | 0.83333 |  | >4 years | Improvement
Memorial Field | Field Lighting | Study options | Replace |  |  | 400 |  | 25 |  |  |  | 425 | Y | [5 empty] | 9 | 3 | 3 | 1 | 1 | 5 | 9 | 3 | 3 | 3 | 6 | 0.83333 | Work on Scope, Look into RCO YAF, Match from Schools, Donations, Volunteers | 12 months | Improvement
Indian Island Park | Improve trail signage and install interpretive/historical interest signs | [17 empty] | 1 | 3 | 3 | 1 | 3 | 2 | 3 | 1 | 3 | 1 | 2.4 | 0.83333 |  | 2 - 4 years | Improvement
Oak Bay Campground | Replace posts at Upper CG | Reconfigure use |  | 12 | [7 empty] | 12 | [6 empty] | 3 | 1 | 1 | 1 | 3 | 2 | 3 | 1 | 3 | 1 | 2.4 | 0.83333 |  | 2 - 4 years | Repair
Quilcene Campground | Playground |  | Replace | [6 empty] | 40 |  | 40 | Y | [5 empty] | 3 | 3 | 1 | 1 | 3 | 2.4 | 3 | 3 | 3 | 3 | 3 | 0.8 |  | 2 - 4 years | Improvement
Gibbs Lake | Enlarge Parking Lots | Horse Trailer and car parking | [16 empty] | 1 | 3 | 3 | 3 | 3 | 2.2 | 3 | 3 | 3 | 1 | 2.8 | 0.78571 |  | 2 - 4 years
North Beach | Restroom |  | Replace | [6 empty] | 50 |  | 50 | Y | [5 empty] | 3 | 3 | 1 | 1 | 1 | 2.2 | 3 | 3 | 3 | 3 | 3 | 0.73333 |  | >4 years | Improvement
HJ Carrol Park | Courts | Resurface | Resuface | [6 empty] | 45 |  | 45 | Y | [5 empty] | 3 | 1 | 3 | 1 | 1 | 2.2 | 3 | 3 | 3 | 3 | 3 | 0.73333 |  | 2 - 4 years | Repair
HJ Carrol Park | Restroom Building | Molly in 2015 | Paint interiors |  | 3 | [6 empty] | 3 | N | [5 empty] | 3 | 1 | 1 | 1 | 1 | 1.8 | 1 | 1 | 9 | 1 | 2.6 | 0.69231 |  | 12 months | Repair
HJ Carrol Park | Courts | Can wait | Repair tire damage, Resurface | 1.4 | [5 empty] | 45 |  | 46.4 | N | [5 empty] | 3 | 1 | 1 | 1 | 3 | 2 | 3 | 3 | 3 | 3 | 3 | 0.66667 |  | 2 - 4 years | Repair
Indian Island Park | Lagoon Parking Lot |  | Restore, modify access | [7 empty] | 250 | 250 | Y | [5 empty] | 9 | 3 | 1 | 1 | 9 | 5.4 | 9 | 9 | 9 | 1 | 8.2 | 0.65854 |  | >4 years | Improvement
Indian Island Park | Redesign and reconfigure Portage shelter area to improve parking and safety | [17 empty] | 1 | 3 | 3 | 1 | 1 | 1.8 | 3 | 3 | 3 | 1 | 2.8 | 0.64286 |  | >4 years | Improvement
Equestrian Park | Race Course | JEA | Install |  |  | 0 | 0 |  |  |  |  | 0 | Y | [5 empty] | 1 | 3 | 3 | 1 | 1 | 1.8 | 3 | 3 | 3 | 1 | 2.8 | 0.64286 |  | >4 years | Improvement
Irondale Beach Park | Picnic Shelter | Because of its location, potential partners, potential for grant funding | Tables/Shelter/Grills |  |  | 0 | [5 empty] | 0 | Y |  | Y |  |  |  | 1 | 3 | 3 | 1 | 1 | 1.8 | 3 | 3 | 3 | 1 | 2.8 | 0.64286 |  | 2 - 4 years | Improvement
Memorial Field | Scoreboard | Replace |  | 8 | [7 empty] | 8 | [6 empty] | 3 | 1 | 1 | 1 | 1 | 1.8 | 3 | 3 | 3 | 1 | 2.8 | 0.64286 |  | 2 - 4 years | Repair
Irondale Beach Park | Toilet | Because of its location, potential partners, potential for grant funding | Vault toilet |  |  |  | 0 |  | 10 |  |  | 10 | Y |  | Y |  |  |  | 1 | 3 | 3 | 1 | 1 | 1.8 | 3 | 3 | 3 | 3 | 3 | 0.6 |  | >4 years | Improvement
Irondale Community Park | B-Ball Court |  | Resurface | [5 empty] | 24 |  |  | 24 | Y | [5 empty] | 3 | 1 | 1 | 1 | 1 | 1.8 | 3 | 3 | 3 | 3 | 3 | 0.6 |  | 2 - 4 years | Repair
Oak Bay Campground | Landscape | Seek Hard Dollars | Surfaces, plants, borders |  | 22 | 2 | 2 | 2 |  |  |  | 28 | Y | [5 empty] | 1 | 3 | 3 | 1 | 1 | 1.8 | 3 | 3 | 3 | 3 | 3 | 0.6 |  | 2 - 4 years | Improvement
Courthouse Park | Tennis Court | Great fundraiser | Resurface and Repair Fence |  |  |  | 30 |  |  |  |  | 30 | Y | [5 empty] | 3 | 3 | 1 | 1 | 3 | 2.4 | 3 | 3 | 9 | 3 | 4.2 | 0.57143 |  | 2 - 4 years | Repair
Indian Island Park | Install Portapot at south Istmus trailhead | [17 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 9 | 1.8 | 0.55556 |  | 12 months | Improvement
Indian Island Park | Improve connection between Lagoon and Isthmus trails | [17 empty] | 1 | 9 | 3 | 1 | 3 | 3.2 | 9 | 3 | 3 | 1 | 5.8 | 0.55172 |  | >4 years | Improvement
HJ Carrol Park | Playground |  | Replace | [6 empty] | 30 |  | 30 | Y | [5 empty] | 1 | 1 | 3 | 1 | 3 | 1.6 | 3 | 3 | 3 | 3 | 3 | 0.53333 |  | 2 - 4 years | Improvement
Chimacum Park | Campground/Park | Possible dog park, bike skills course, walking/running trail | Restore, repurpose, or decommission the entire park | [6 empty] | 25 |  | 25 | Y | [5 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 9 | 9 | 9 | 6 | 0.5 |  | 2 - 4 years | Improvement
Gibbs Lake | Caretakers House | Renovate |  |  |  |  | 50 |  |  |  |  | 50 | Y | [5 empty] | 3 | 1 | 1 | 1 | 3 | 2 | 3 | 3 | 9 | 3 | 4.2 | 0.47619 |  | >4 years | Improvement
Trailhead Park | Bike Skills Area | Partners? | Mountain Bikers |  | 8 | 8 | [5 empty] | 16 | Y | [5 empty] | 1 | 3 | 3 | 1 | 3 | 2 | 3 | 9 | 3 | 3 | 4.2 | 0.47619 | No volunteer group at this time | >4 years | Improvement
Oak Bay Campground | RV Dump | Seek Hard Dollars | Install | [8 empty] | 0 | Y | [5 empty] | 1 | 9 | 3 | 1 | 3 | 3.2 | 9 | 9 | 3 | 3 | 7.2 | 0.44444 |  | >4 years | Improvement
Hicks Park | Restore Shoreline |  | Remove Hard Armour | [5 empty] | 125 |  |  | 125 | Y | [5 empty] | 1 | 9 | 1 | 1 | 3 | 2.8 | 9 | 9 | 3 | 3 | 7.2 | 0.38889 |  | >4 years | Improvement
Memorial Field | Maint Shed |  | Paint, insulate, heater | [6 empty] | 8 |  | 8 | Y | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 9 | 3 | 3.2 | 0.3125 |  | 12 months | Repair
Lake Leland | Campground Utilities |  | Water and power | [6 empty] | 100 |  | 100 | Y | [5 empty] | 1 | 3 | 3 | 3 | 1 | 2 | 9 | 3 | 3 | 9 | 6.6 | 0.30303 |  | >4 years | Improvement
Memorial Field | Wash St Fence | Urgent | Replace Washington St fence with wrought iron fence |  |  | 50 | [5 empty] | 50 | Y | [5 empty] | 3 | 1 | 1 | 1 | 3 | 2 | 9 | 9 | 9 | 3 | 8.4 | 0.2381 | Jane recruiting donors | 12 months | Improvement
North Beach | Boat Ramp | Existing structure is impeding replenishment of beach and eel grass. Seek Partner | Remove, restore beach | [7 empty] | 25 | 25 | Y | [5 empty] | 1 | 1 | 1 | 1 | 3 | 1.2 | 3 | 9 | 9 | 1 | 5.2 | 0.23077 |  | 2 - 4 years | Improvement
HJ Carrol Park | Third Field | RCO | Install | [6 empty] | 155 |  | 155 | Y |  | Y |  |  |  | 1 | 3 | 3 | 1 | 1 | 1.8 | 9 | 3 | 9 | 9 | 7.8 | 0.23077 |  | >4 years | Improvement
Chimacum Park | Toilets | Volunteers needed | Repair to preserve | 2 | [7 empty] | 2 | N |  |  | Y |  | Done | [5 empty] | 0 |  |  |  |  | 0 | 0 |  | Done | Repair | 2015-06-01
Indian Island Park | Shelter Fix Up | Roads Crew | Remove old grill, replace new grill, surface with rock, new picnic tables | [8 empty] | 0 | N |  |  | Y |  | Done | [5 empty] | 0 |  |  |  |  | 0 | 0 |  | Done | Repair | 2015-07-01
Indian Island Park | Toilet | Volunteers needed | Repair and paint | 2 | [7 empty] | 2 | N |  |  | Y |  | Done | [5 empty] | 0 |  |  |  |  | 0 | 0 |  | Done | Repair | 2015-06-01
Memorial Field | Concession | Irene in 2015 | Repair Siding and paint | 2 | [6 empty] | 20 | 22 | N |  |  |  |  | Done | [5 empty] | 0 |  |  |  |  | 0 | 0 |  | Done | Repair
Hicks Park | Toilet | Volunteers planning for Easter Weekend | Door, roof, repair and paint | 3 | [7 empty] | 3 | N |  |  | Y |  | Done | [5 empty] | 0 |  |  |  |  | 0 | 0 |  | Done | Repair
Indian Island Park | Improve line of sight at Portage Shelter entrance to reduce risk of accidents |  | Clear line of sight from entrance to bridge and from entrance to uphill curve east of drive | [12 empty] | Y | 2015-10-01 | Done | [5 empty] | 0 |  |  |  |  | 0 | 0 | Being done by IIP volunteers Dennis Burk and Greg Graves | Done | Repair | 2016-03-01
Oak Bay Campground | Replace posts at Upper CG | Reconfigure for ease of maintenance | [29 empty] | 2 - 4 years

## Goals & Objectives
Goals and Objectives from updated PROS Plan
Administrative Goal #1 SUSTAINABLE RESOURCES AND COORDINATED MANAGEMENT: Create effective and efficient methods of acquiring, developing, operating and maintaining facilities and programs that accurately distribute costs and benefits to public and private interests.
Facilities and Program Goal #1: COUNTY-WIDE PROGRAMS AND SERVICES: Develop focused recreation programs that utilize and support existing facilities, provide the greatest benefit and generate the highest level of self-sustaining fee revenue.
Facilities and Proram Goal #2: RECREATIONAL FACILITIES: Maintain and improve those resources currently in the system. When financially feasible and sustainable, develop a high quality, diversified recreation system that provides for all age and interest groups.
Facilities and Program Goal #3: DESIGN AND ACCESS STANDARDS: Design and develop facilities that are accessible, safe, and easy to maintain, with life cycle features that account for long-term costs and benefits.
Historial and Cultural Resources Goal #1: HISTORICAL RESOURCES: As is feasible and sustainable, develop a high quality, diversified park system that preserves significant historical opportunity areas and features.
Historical and Cultural Resources Goal #2: MANMADE ENVIRONMENTS AND FEATURES: Incorporate interesting manmade environments, structures, activities and areas into the park system to preserve these features and provide a balanced park, recreation and open space experience
Historical and Cultural Resources Goal #3: CULTURAL ARTS PROGRAMS AND RESOURCES: Provide high quality parks and facilities that can be utilized by existing organizations and schools in the implementation and provision of cultural programs.